# Electrolyzer Vendor FAT / SAT Acceptance Framework

## Purpose

This document establishes a mandatory Factory Acceptance Test (FAT) and Site Acceptance Test (SAT) framework for all electrolyzer and hydrogen process equipment procurements. It is designed to be contract-ready, enforceable, and repeatable across vendors. This framework protects capital, enforces transparency, and eliminates performance ambiguity before funds are released or equipment is energized on site.

This is not guidance. This is a gate.

## Scope

Applies to:

- PEM, SOEC, and alkaline electrolyzers

- Hydrogen purification, drying, and compression skids

- Integrated thermal recovery and electrical balance-of-plant systems

This framework must be incorporated into:

- RFPs

- Vendor technical schedules

- Purchase Orders

- EPC contracts

## Definitions

FAT: Factory Acceptance Test performed at vendor facility prior to shipment

SAT: Site Acceptance Test performed after installation at owner site

COA: Certificate of Analysis from independent laboratory

Nameplate: Contracted continuous output rating

## 1. Factory Acceptance Test (FAT)

### 1.1 General Requirements

- FAT is mandatory and witnessed by owner or owner-appointed third party

- No shipment authorized until FAT acceptance is issued in writing

- All raw data belongs to owner

### 1.2 Electrical and Stack Characterization

- Full polarization curve across operating range

- As-built stack impedance measurement

- Cell-level voltage distribution logging

- Sampling rate >= 1 Hz

### 1.3 Startup and Operating Behavior

- Cold start to nameplate load

- Hot restart after >= 2 hour soak

- Controlled shutdown and purge sequence

### 1.4 Dynamic Load Testing

- Step changes: 10%, 25%, 50%, 75%, 100%

- Linear ramp profiles (fast and slow)

- PV-simulated variable input profile

- Minimum 15-minute hold at each plateau

### 1.5 Impurity Stress Testing

Controlled injection of the following into feed stream within vendor-stated limits:

- Ammonia (NH3)

- Carbon monoxide (CO)

- Carbon dioxide (CO2)

Required observations:

- Voltage deviation

- Protection response

- Time to recovery to baseline

### 1.6 Endurance Run

- Continuous 72-hour operation at nameplate

- Continuous logging of:

  - Stack voltage and current

  - Temperatures

  - Pressures

  - Flow rates

  - Power consumption

  - Hydrogen purity

  - Alarm and trip states

### 1.7 Safety and Interlocks

- Emergency stop verification

- Over-temperature and over-pressure trips

- Hydrogen leak detection

- Valve fail-safe behavior

## 2. FAT Deliverables

Required prior to shipment:

- Complete raw data logs (CSV or equivalent)

- Instrument calibration certificates

- Independent laboratory COA for hydrogen purity

- Signed FAT report with pass/fail table

Failure to deliver any item halts shipment authorization.

## 3. Site Acceptance Test (SAT)

### 3.1 Reproduction of FAT Profiles

- Repeat dynamic ramp and step tests

- Compare results directly against FAT data

### 3.2 Electrical Integration

- Verification of DC/AC interfaces

- Grounding and harmonic behavior

- Ride-through and restart behavior

### 3.3 Thermal Integration

- Heat recovery loop performance

- Supply and return temperature verification

- Delta-T and flow validation

- No cross-contamination or fouling

### 3.4 Controls and SCADA

- Full I/O checkout

- Alarm setpoint validation

- Cause-and-effect verification

- Historian tag mapping and retention confirmation

### 3.5 Degradation Baseline

- Continuous 7-day run at nameplate

- Polarization curve at start and end

- Voltage drift per cell recorded

## 4. Acceptance Criteria and Remedies

| Test Item | Requirement | Evidence | Remedy if Failed |
| --- | --- | --- | --- |
| Hydrogen Output | >= Contracted kg/hr | FAT/SAT logs | Vendor retrofit or rejection |
| Energy Intensity | <= Contracted kWh/kg | FAT/SAT logs | Price reduction or retrofit |
| Hydrogen Purity | Meets contract spec | Independent COA | Re-test or rejection |
| Voltage Spread | <= Contracted mV/cell | Stack logs | Stack service |
| Startup Times | Within contract limits | Logs | Controls modification |
| Impurity Recovery | Full recovery within limit | Logs | Component replacement |
| 7-Day Degradation | Within allowable drift | Logs | Warranty extension |

No partial acceptance. All criteria must pass.

## 5. Data Ownership and Transparency

- Owner retains ownership of all test data

- No down-sampling or filtering permitted

- Time-synchronized data required

- Vendor summaries do not replace raw logs

## 6. Warranty Linkage

- Warranty start date equals SAT acceptance date

- Replaced components reset burn-in period

- Performance warranties tied to FAT/SAT metrics

## 7. Commercial Controls

- Shipment contingent on FAT acceptance

- Milestone payments contingent on SAT acceptance

- Persistent failure triggers rejection or price renegotiation

## 8. Document Control

This framework is a controlled technical standard. Deviations require written approval by owner executive authority.

End of Document